**PUBLIC SECTOR REFORM SECRETARIAT**

**OFFICE OF THE PRESIDENT**

**GHANA OPEN GOVERNMENT PARTNERSHIP (OGP) FOURTH NATIONAL ACTION PLAN (NAP-4)**

**MoCD/NITA MONITORING REPORT**

|  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | **THEMATIC AREA: TECHNOLOGY AND INNOVATION** | | | | | | | |
| **COMMITMENTS/**  **MILESTONES** | **INDICATORS** | **DEFINITION** | **BASELINE**  **2021** | **END TARGET**  **2023** | **PROGRESS AS AT JUNE, 2023** | **MEANS OF VERIFICATION** | **REMARKS (NEXT STEPS)** | **RESPONSIBLE MDA** |
| **Commitment 5.1.1:** Ensure that the delivery of public services is improved through the sustained implementation of the Ghana Open Data Initiative | Number of public institutions implementing Ghana Open Data Initiative in the delivery of services. | GODI is a government platform to ensure public accessibility of all government data. | GODI portal  20 MDAs strained to upload data onto the portal | 50 public institutions are implementing the Open Data Initiative by end of 2023 | Securing funding from e-Transform to organise data upload training for focal persons in MDAs | No. of datasets on the Data.gov.gh portal | Talk with Experts to enhance the portal with analytics and AI capabilities | **Responsible Institutions**  Ministry of Communications and Digitalization  **Collaborating Institutions**  Kwame Nkrumah University of Science and Technology (KNUST)  University of Professional Studies Accra (UPSA)  Ashesi University  Ghana Open Data Alliance, Ghana Academic and Research Network  National Council on Persons with Disability |
| **Milestones Activities**  **5.1.1.1:** Engage in public awareness activities about the open data portal with all stakeholders and make portal accessible to persons with disability | Meetings held with key stakeholders on the open data portal with portals accessible to PWDs  (Yes, No) | -----do--------- | No | Three activities in Accra, Kumasi and Tamale and train PWDs | Organised training for Executive Secretary ,Management and staff of National Council for Persons with Disability | Report of the training. | To secure API and applications for disabilities. |
| **5.1.1.2**: Ensure that data from critical sectors of the economy such as agriculture and industry are regularly uploaded on their portals in a disaggregated format that is more useful to the data consuming public. | Data from critical sectors of the economy including agriculture and industry uploaded on their portals and in format useful and accessible to the public  (Yes, No) | --------do---------- | No 20 | Letters sent to 20 Institutions to upload data. | Received some responses from Institutions written to | Letters | Developed excel application programmed to disaggregate data in the right format and sent to the Institutions. |
| **5.1.1.3:** Support regulatory agencies and licensing authorities to develop data collection /data set standard for their agencies and build an interoperable digital system | Regulatory agencies and licensing authorities have developed data collection /data set standard for their agencies and build an interoperable digital system  (Yes, No) | Data from regulatory agencies must be in an acceptable format | Secretariate set up at NITA to clean datasets before upload | Agencies and institutions deploy an interoperable digital system | None | Participant/attendance sheet, report pictures and videos | Developed excel application programmed to disaggregate data in the right format and sent to the Institutions |
| **5.1.1.4:** Data systems personnel trained to manage the various data systems | Number of data systems personnel trained with training report |  | No. 0 | 15 data systems personnel trained in 2023 | Three data experts trained as trainers | Training documents, pictures, attendance sheets | Training scheduled for October 2023 |
| **5.1.1.5** Direct research statistics and information management directorate of the Ministries, Departments and Agencies lead data set /data collection teams | The research statistics and information management directorate of MDAs are taking lead role in data collection  (Yes, No) | Identify research statistics and information management directorate as focal persons in GODI | None | 100 focal persons trained | Preparations towards training of 100 focal persons. This includes securing funding, training, facilitators, etc. | Training documents, pictures, attendance sheets, reports | Training to be accomplished by end of year 2023 |
| **5.1.1.6** Provide specific annual budget allocation Ghana Open Data Initiative (GODI) and support GODI secretariat to secure the active involvement of the academic and research community in GODI | GODI provided with specific annual budget allocation  (Yes, No) | NITA to ensure annual budget allocation for GODI activities | - | GODI activities and budget captured in NITA annual budget | Budget allocated for GODI capacity building and Hackathon | Utilisation certificate/voucher | Capacity building to be done in October 2023 |
|  | GODI Secretariat has taken measures to ensure the involvement of the academic and research community in GODI  (Yes, No) | GODI Secretariat has taken measures to ensure the involvement of the academic and research community | None | 5 tertiary institutions to be involved in GODI activities | Written proposals for funding to embark on outreach to 5 universities | Pictures of site visits, videos, reports | Outreach to be done before end of 2023 |
| **5.1.1.7** Ensure that National Open Data sharing policy is implemented, and NITA will be involved in the design, identification, and procurement of digital platform | The National Open Data Sharing policy implemented  (Yes, No) | Development of Open Data Sharing Policy | Drafted National Open Data Sharing Policy | Open Data Sharing Policy developed for implementation | Awaiting approval for implementation | Open Data Sharing Policy developed | Conduct publicity and awareness activities |
|  | NITA participated in the design, identification, and procurement of digital platform  (Yes, No) | A means to ensure coherence in procurement and enhance security and privacy of digital platforms and accessories. | - | MDAs/MMDAs comply with the regulatory role of NITA | Knowledge Management platform for the Social Cohesion (SOCO) Project, of the Ministry of Local Government | Invitations/request, pictures, attendance etc | Strengthen conformance with grant of approval before project or procurement is undertaken. | MoCD-NITA  All MMDAs, MDAs / Public Service |