**PUBLIC SECTOR REFORM SECRETARIAT**

**OFFICE OF THE PRESIDENT**

**GHANA OPEN GOVERNMENT PARTNERSHIP (OGP) FOURTH NATIONAL ACTION PLAN (NAP-4)**

**MoCD/NITA MONITORING REPORT**

|  |  |
| --- | --- |
|  | **THEMATIC AREA: TECHNOLOGY AND INNOVATION** |
| **COMMITMENTS/****MILESTONES** | **INDICATORS** | **DEFINITION** | **BASELINE****2021** | **END TARGET** **2023** | **PROGRESS AS AT JUNE, 2023** | **MEANS OF VERIFICATION** | **REMARKS (NEXT STEPS)** | **RESPONSIBLE MDA** |
| **Commitment 5.1.1:** Ensure that the delivery of public services is improved through the sustained implementation of the Ghana Open Data Initiative | Number of public institutions implementing Ghana Open Data Initiative in the delivery of services.  | GODI is a government platform to ensure public accessibility of all government data. |  GODI portal20 MDAs strained to upload data onto the portal | 50 public institutions are implementing the Open Data Initiative by end of 2023 | Securing funding from e-Transform to organise data upload training for focal persons in MDAs  | No. of datasets on the Data.gov.gh portal | Talk with Experts to enhance the portal with analytics and AI capabilities  | **Responsible Institutions** Ministry of Communications and Digitalization**Collaborating Institutions**Kwame Nkrumah University of Science and Technology (KNUST)University of Professional Studies Accra (UPSA)Ashesi UniversityGhana Open Data Alliance, Ghana Academic and Research NetworkNational Council on Persons with Disability |
| **Milestones Activities****5.1.1.1:** Engage in public awareness activities about the open data portal with all stakeholders and make portal accessible to persons with disability  | Meetings held with key stakeholders on the open data portal with portals accessible to PWDs(Yes, No) | -----do--------- | No | Three activities in Accra, Kumasi and Tamale and train PWDs | Organised training for Executive Secretary ,Management and staff of National Council for Persons with Disability  | Report of the training. | To secure API and applications for disabilities. |
| **5.1.1.2**: Ensure that data from critical sectors of the economy such as agriculture and industry are regularly uploaded on their portals in a disaggregated format that is more useful to the data consuming public.  |  Data from critical sectors of the economy including agriculture and industry uploaded on their portals and in format useful and accessible to the public(Yes, No) | --------do---------- | No 20 | Letters sent to 20 Institutions to upload data. | Received some responses from Institutions written to | Letters | Developed excel application programmed to disaggregate data in the right format and sent to the Institutions. |
| **5.1.1.3:** Support regulatory agencies and licensing authorities to develop data collection /data set standard for their agencies and build an interoperable digital system | Regulatory agencies and licensing authorities have developed data collection /data set standard for their agencies and build an interoperable digital system(Yes, No) | Data from regulatory agencies must be in an acceptable format | Secretariate set up at NITA to clean datasets before upload | Agencies and institutions deploy an interoperable digital system | None | Participant/attendance sheet, report pictures and videos | Developed excel application programmed to disaggregate data in the right format and sent to the Institutions |
| **5.1.1.4:** Data systems personnel trained to manage the various data systems | Number of data systems personnel trained with training report |  | No. 0 | 15 data systems personnel trained in 2023 | Three data experts trained as trainers | Training documents, pictures, attendance sheets | Training scheduled for October 2023 |
| **5.1.1.5** Direct research statistics and information management directorate of the Ministries, Departments and Agencies lead data set /data collection teams | The research statistics and information management directorate of MDAs are taking lead role in data collection(Yes, No) | Identify research statistics and information management directorate as focal persons in GODI | None  | 100 focal persons trained | Preparations towards training of 100 focal persons. This includes securing funding, training, facilitators, etc. | Training documents, pictures, attendance sheets, reports | Training to be accomplished by end of year 2023 |
|  **5.1.1.6** Provide specific annual budget allocation Ghana Open Data Initiative (GODI) and support GODI secretariat to secure the active involvement of the academic and research community in GODI | GODI provided with specific annual budget allocation(Yes, No) | NITA to ensure annual budget allocation for GODI activities | - | GODI activities and budget captured in NITA annual budget | Budget allocated for GODI capacity building and Hackathon  | Utilisation certificate/voucher  | Capacity building to be done in October 2023 |
|  | GODI Secretariat has taken measures to ensure the involvement of the academic and research community in GODI(Yes, No) | GODI Secretariat has taken measures to ensure the involvement of the academic and research community  | None | 5 tertiary institutions to be involved in GODI activities | Written proposals for funding to embark on outreach to 5 universities  | Pictures of site visits, videos, reports | Outreach to be done before end of 2023 |
| **5.1.1.7** Ensure that National Open Data sharing policy is implemented, and NITA will be involved in the design, identification, and procurement of digital platform | The National Open Data Sharing policy implemented(Yes, No) | Development of Open Data Sharing Policy | Drafted National Open Data Sharing Policy | Open Data Sharing Policy developed for implementation | Awaiting approval for implementation | Open Data Sharing Policy developed  | Conduct publicity and awareness activities |
|  | NITA participated in the design, identification, and procurement of digital platform(Yes, No) | A means to ensure coherence in procurement and enhance security and privacy of digital platforms and accessories. | - | MDAs/MMDAs comply with the regulatory role of NITA | Knowledge Management platform for the Social Cohesion (SOCO) Project, of the Ministry of Local Government | Invitations/request, pictures, attendance etc | Strengthen conformance with grant of approval before project or procurement is undertaken. | MoCD-NITAAll MMDAs, MDAs / Public Service |